Implementation Plan

Software Bridge: Hi-Fi Rose RS520 ↔ URC Total Control ↔ Josh AI

Prepared for: Phil  ·  Date: 2026-05-27

# 1. Executive Summary

This document specifies a phased plan to build a software bridge that allows a URC Total Control system to fully control a Hi-Fi Rose RS520 network streamer/integrated amplifier, and — in a later phase — to expose that same control surface to Josh AI for natural-language voice automation.

Per stakeholder direction, the bridge is deployed inside the URC Total Control processor as a custom IP driver authored in Accelerator 3. The initial control direction is URC → RS520. Two-way feedback and Josh AI integration follow in later phases.

Key technical reality: Hi-Fi Rose has not published an official RS520 API. All known programmatic control is via a reverse-engineered HTTP/JSON interface on TCP port 9283 (documented in this plan). The interface has changed across firmware releases (most recently August 2025), so the plan includes a hard requirement for a firmware-pinning policy and an isolation layer so that downstream Rose firmware drift never breaks the URC system at the dealer level.

# 2. System Topology

Three peers, one local LAN segment:

- Hi-Fi Rose RS520 — the controlled endpoint. Static IP, reachable on port 9283 (HTTP/JSON).

- URC Total Control processor (MRX-class) — the controller of record. Runs the custom IP driver.

- Josh AI Core — the natural-language layer. Issues high-level intents (“play Roon in the listening room”).

Control flow priorities, in order:

- URC handheld/keypad → RS520 (Phase 1).

- RS520 state → URC two-way feedback (Phase 2).

- Josh AI voice → URC → RS520 (Phase 3).

- RS520 now-playing → Josh AI UI (Phase 4, partnership-gated).

# 3. Control-Surface Audit

## 3.1 Hi-Fi Rose RS520

Hi-Fi Rose's stated position (community channels, August 2025) is that no public API is available; the manufacturer is “considering future options.” Available paths:

- HTTP/JSON on port 9283 — reverse-engineered; controls power, volume, input source; partial telemetry.

- DLNA/UPnP MediaRenderer — native; supports basic transport for DLNA-served streams; does NOT control physical inputs.

- Roon RAAT — native Roon Ready; full transport when source = Roon.

- Spotify Connect, AirPlay, Bluetooth A2DP — source-side, not control-side.

- Bluetooth remote + external IR receiver — hardware fallback; IR codes not publicly published.

Recommended primary path: HTTP/JSON on :9283 (rich control), with UPnP MediaRenderer as a transport fallback for play/pause/skip on streamed sources. IR is held in reserve as a worst-case fallback for power if Rose changes the JSON shape again.

## 3.2 URC Total Control / Accelerator 3

URC supports custom IP drivers authored in Accelerator 3's “My Database → New Driver” workflow. Drivers can be IR, RS-232, or IP. IP drivers send command strings over the network from the processor to the target device, and two-way feedback is handled by “Universal Parse Data” — a parser that extracts state values from device responses. Per URC documentation, custom parse-data work is gated to expert/dealer programmers.

Driver components we will build out:

- Brand: HiFi Rose. Model: RS520. Device Type: AV Receiver / Streamer.

- Control type: IP.

- Functions: Power On, Power Off, Power Toggle, Volume Up, Volume Down, Set Volume (0-100), Mute Toggle, Source Select (5 inputs), Transport Play/Pause/Stop/Next/Prev (Phase 2).

- Two-way parse-data: power state, current source, current volume (telemetry-dependent).

- Power-on delay: 4000ms (Rose boot lag between sleep wake and first command accept).

- Interstep delay: 150ms.

## 3.3 Josh AI

Josh AI does not publish an open third-party SDK. Custom drivers are produced through their “Nimble DevSuite” on a partnership basis. Their fully certified driver path is Control4. There is no shipping URC-to-Josh certified driver as of this writing.

Three viable integration vectors, ranked:

- URC pass-through. Josh issues HTTP/voice intents that map to URC system macros; URC already controls the RS520. Lowest risk; uses URC's existing third-party command surface.

- Direct bridge. Josh → bridge service → RS520. Requires Josh partnership engagement to author a custom driver.

- Roon proxy. Josh has a Roon driver; if Rose is in Roon Ready mode, Josh can control transport but cannot switch RS520 physical inputs.

# 4. Recommended Architecture

The user has chosen the URC Total Control processor as the deployment target. There are two valid topologies for that choice. We recommend Option B for production:

## 4.1 Option A — Direct (URC driver → RS520)

URC custom IP driver speaks HTTP/JSON directly to RS520 on :9283.

- Pros: Single artifact. No additional hardware. Lowest moving parts.

- Cons: Rose firmware changes break the URC driver in the field. Each break requires a dealer truck-roll to deploy a new driver image. No place to log or trace traffic for debug.

## 4.2 Option B — Recommended: Driver + Isolation Bridge

URC custom IP driver speaks a STABLE, internal HTTP/JSON contract to a small bridge service running on a dedicated Pi/NUC (or as a Docker container on the homeowner's NAS). The bridge translates the stable contract into Rose's reverse-engineered protocol.

- Pros: Rose firmware drift is absorbed by the bridge — the URC programmed system never changes. Bridge can do health checks, retries, request coalescing, and log every transaction for support.

- Pros: Bridge is the same surface Josh AI will eventually hit, so Phase 3 work is amortized.

- Cons: Adds one always-on appliance to the rack. Bridge is the single point of failure for control (but RS520 is still locally usable).

## 4.3 Bridge Service Internal Contract

The URC driver and (later) Josh AI both speak this stable contract to the bridge:

| Method | Path | Body / Notes |
| --- | --- | --- |
| GET | /v1/health | Returns 200 if bridge can reach RS520. Used by URC ping driver. |
| GET | /v1/state | Returns {power, source, volume, playing}. Cached/polled by bridge. |
| POST | /v1/power | {"state":"on"¦"off"¦"toggle"} |
| POST | /v1/source | {"input":"LINE_IN"¦"OPTICAL"¦"EARC"¦"USB"¦"AES_EBU"¦"STREAMING"} |
| POST | /v1/volume | {"level":0..100} OR {"delta":±n} |
| POST | /v1/transport | {"cmd":"play"¦"pause"¦"stop"¦"next"¦"prev"} |

# 5. RS520 Endpoint Reference (Reverse-Engineered)

Captured from packet inspection of the Rose Connect PC application and validated against the open-source Home Assistant integration (cornusmas87/hifirose_rs520). All endpoints are HTTP POST to http://<rs520-ip>:9283. Confirmed against RS520 firmware 5.9.02. THE SHAPE OF THESE ENDPOINTS HAS CHANGED BETWEEN FIRMWARE RELEASES AND IS EXPECTED TO CHANGE AGAIN.

### Power

POST /remote_bar_order

{ "barControl": "remote_bar_order_sleep_on_off", "value": "1" }   // on

{ "barControl": "remote_bar_order_sleep_on_off", "value": "-1" }  // off

### Volume

POST /volume

{ "volumeType": "volume_set", "volumeValue": 0..100 }

### Source select

POST /input.mode.set

{ "funcMode": 1 }   // 1=LINE IN, 2=OPTICAL, 3=eARC, 4=USB, 5=AES/EBU

### State telemetry

POST /get_current_state   body: {}

response.data: { volume, tempArr:["funcMode:N", ...], isPlaying, isPowerOn }

Known limitations on the telemetry endpoint: volume reads as 0 in certain states (slider drift in HA integration); funcMode is embedded in a string array; no album-art or now-playing metadata is exposed.

# 6. Phased Implementation Plan

## Phase 0 — Discovery & Validation (Week 1)

Goal: prove every endpoint above works on YOUR RS520, with YOUR firmware.

- Assign RS520 a static DHCP reservation. Confirm port 9283 is reachable from the URC processor's subnet.

- Run the discovery probe script (Phase 0 deliverable) that POSTs each endpoint and logs response shape.

- Pin the current Rose firmware version. Document the build number. Disable auto-updates if possible.

- Confirm URC Accelerator 3 version and dealer-portal access. Confirm processor model (MRX-8/10/20).

- Exit criteria: all six bridge-contract endpoints succeed end-to-end against a real RS520 via curl.

## Phase 1 — URC → RS520 Minimum Viable Driver (Weeks 2–4)

Goal: A handheld remote button moves the RS520. One-way control only.

- Stand up the bridge service in a development container. Implement /v1/power, /v1/source, /v1/volume against the Rose endpoints.

- Author the URC custom IP driver in Accelerator 3 → My Database → New Driver.

- Driver functions wired: PowerOn, PowerOff, PowerToggle, VolumeUp, VolumeDown, Mute, Input1..Input5.

- Power-on delay set to 4000ms; interstep delay 150ms. Confirm with stress test (rapid source changes).

- Assign the driver to a room. Map handheld buttons. Download to processor.

- Exit criteria: all front-panel functions controllable from a URC TRC remote with no user-visible failures over a 24-hour soak.

## Phase 2 — Two-Way Feedback (Weeks 5–6)

Goal: The URC UI shows the RS520's true current state, even when the user touches the Rose physically.

- Bridge polls /get_current_state every 1s; coalesces into /v1/state.

- URC driver Universal Parse Data block extracts power, source, volume from a single bridge JSON response.

- Two-way bindings drive on-screen indicators (current input badge, mute state, volume slider).

- Edge case: telemetry-volume returns 0 in some states. Bridge holds last-known-good and only emits transitions.

- Exit criteria: manually changing source on the RS520 front panel updates the URC TRC screen within 2 seconds.

## Phase 3 — Hardening & Failure Modes (Week 7)

- Bridge implements exponential backoff on RS520 connect failures; surfaces health via /v1/health.

- URC driver pings /v1/health every 30s; raises a system flag if bridge is down.

- Add a Global Caché iTach IP2IR (or similar) for emergency power-off via IR if the JSON API is broken by firmware.

- Snapshot the bridge configuration and Rose firmware version into git; tag the working pairing.

- Exit criteria: bridge container can be restarted, RS520 can be power-cycled, network can blink — system recovers without user intervention.

## Phase 4 — Josh AI Integration (Weeks 8–12, partnership-gated)

Two parallel tracks. Pursue whichever clears procurement first.

- Track A (URC pass-through): Define a small set of Josh voice intents (“put the listening room on Roon,” “mute the listening room”). Each maps to a URC system macro that the existing driver already serves. No new code on the RS520 path.

- Track B (Direct bridge integration): Engage Josh AI partnerships, request Nimble DevSuite access, author a Josh custom driver against the existing /v1/* bridge contract.

- Exit criteria: at least one voice intent (“mute the listening room”) executes end-to-end through Josh.

# 7. Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Rose firmware changes JSON shape | Bridge breaks; control lost | Pin firmware; auto-update OFF; bridge versioned per Rose build; iTach IR fallback for power |
| URC dealer-cert required | Cannot deploy driver to processor | Confirm dealer access in Phase 0; identify partner dealer if needed |
| Josh AI partnership delay | Phase 4 stalls | Track A (URC pass-through) carries voice control until Track B clears |
| Bridge appliance fails | URC ↔ RS520 control lost | Bridge is stateless; runs from read-only image; spare cold-standby on shelf |
| Volume telemetry unreliable | URC slider drifts from true value | Treat URC as authority; suppress display when telemetry =0; do not echo Rose physical knob |
| LAN isolation/VLAN | URC cannot reach RS520 or bridge | Confirm all three peers on the same VLAN; document firewall exceptions |

# 8. Open Questions

- Is the URC dealer relationship in place to download the custom driver to the processor? If not, who is the partner dealer?

- Will the bridge appliance run on existing home infrastructure (NAS, Pi) or do we procure a dedicated fanless box?

- Should the Phase 4 Josh AI work begin in parallel with Phase 1, given the long partnership lead time?

- Is transport metadata (track title, album art) a must-have for Phase 2, or acceptable to defer until Rose ships a public API?

- How many physical inputs does the installation actually use? (Affects how many source-select macros to expose.)

# 9. Deliverables Checklist

- Discovery probe script (Node or Python). Runs against RS520 IP; emits a JSON report of supported endpoints.

- Bridge service (containerized). Implements the /v1/* contract above. Versioned; tagged per Rose firmware.

- URC Accelerator 3 driver package (.urcdriver or equivalent export). Imports into My Database.

- Two-way Universal Parse Data definition (XML/script per URC convention).

- Operations runbook: how to restart the bridge, how to roll back, how to swap in the iTach IR fallback.

- Josh AI intent map (Phase 4): the voice-to-macro lookup table for Track A.

# 10. Sources & References

- HiFi Rose RS520 owner's manual — hifirose.com / sarte-audio.com archived PDF.

- Community Home Assistant integration — github.com/cornusmas87/hifirose_rs520 (validated endpoints on firmware 5.9.02).

- HiFi Rose community thread on Home Assistant integration — community.roseaudio.kr (manufacturer position: no public API yet).

- URC Knowledge Base: Basics of Driver Creation — urcfaq.knowledgeowl.com.

- URC Accelerator 3 product page and update history — urcportal.com.

- Josh.ai integrator page and Control4 certified driver announcement — josh.ai.